## M5(P1) Web Panel
Bug No. | Bug Type | Severity | Module Name | Bug Title | Steps to Reproduce Bug | Bug Description | Dev / QA Bug Status | Assigned To | Issue Image/Video | Dev. Comment | QA Comment
001 | Functional | Major | Portfolio Location | Getting server not respoding error message. |  | Actual Result: Getting server not responding when try to add the portfolio location. Expected Result: Server not responding error message should not display and user able to add the portfolio location. | QA Approved | Hitarth | https://prnt.sc/SWrFCVVqC_A3
002 | Functional | Minor | Portfolio Location >> Tenant | Valdation message is not displaying in red color. |  | Actual Result: Lease expiry date - Validation message for required field is not displaying in red color. Expected Result: Validation message should dsiplay in red color. | QA Approved | Jeet | https://prnt.sc/8PDstBq8VCfG
003 | Functional | Minor | Portfolio Location >> Tenant | Field color is not proper. |  | Actual Result: Lease expiry date - field color is displaying in red color while validation message is displayed. Expected Result: Lease expiry date field should display in black color while validation is displayed. | QA Approved | Jeet | https://prnt.sc/9E4umFa0Sxbm
004 | Functional | Minor | Portfolio Location >> Tenant | Blank is displaying |  | Actual Result: Room & Floor Number - View - Blank is displaying when floor and room number is not added. Expected Result: Dash (-) should display when room and floor number are not added. | QA Approved | Jeet | https://prnt.sc/b_d6RfVurVtG
005 | Functional | Minor | Portfolio Location | Validation message is displaying. |  | Actual Result: Room & Floor Number - Add & Update - Validation message is displaying for room and floor number. Expected Result: Validation message should not display for room and floor number as it is optional. | QA Approved | Hitarth | https://prnt.sc/R7nVgWNOSYi8 https://prnt.sc/qjFozQgcpx-2
006 | Functional | Minor | Portfolio Location | Room and floor number not displaying proper. |  | Actual Result: Room & Floor Number - View - Text limit are not added into room and floor number. Exoected Result: Text limit or dot should added into room and floor number field when long numbers are entered by the user. | QA Approved | Hitarth | https://prnt.sc/s8_rJW4QPKVY https://prnt.sc/o99JBW7Ar75v
007 | Design | Minor | Portfolio Location >> Tenant | Lease expiry date is not in proper aligment. |  | Actual Result: Listing - Lease expiry date field and added date is not in proper alignment in listing page. Expected Result: Lease expiry date field and added date should display in one line on listing page. | QA Approved | Jeet | https://prnt.sc/--zdmL1VBVa5
008 | Functional | Major | Portfolio Location >> Tenant | Not able to uodate the lease expiry date. |  | Actual Result: When entered the date manually or select from calander then lease expiry date is not updating and getting "Please enter numeric value" error. Precondition: room and floor number not added. Expected Result: Error message should not display and user able to update the lease expiry date when room & floor number are not added as it is optional. | QA Approved | Jeet | https://prnt.sc/_oG1ST8DREB6 Reopen - https://prnt.sc/DmAnjg7zRmA8
009 | Functional | Major | Portfolio Location >> Tenant | Call center access displaying already selected after unselecting the checkbox. |  | Actual Result: Call center access - Update - When unselect the checkbox and edit the details then check box is displaying already selected. Expected Result: When call center access given by the fm admin then checkbox should be selected and when not given the call center access then check box should be unselected. | QA Approved | Pradip | https://prnt.sc/_9NdRNE4dEHn
010 | Functional | Minor | Portfolio Location >> Assets | Text is not proper. |  | Actual Result: Text in floor field is not proper. Expected Result: ADD/Listing/Update/View Page - It should be "Floor No" instead of floor. | QA Approved | Jeet | https://prnt.sc/99z6Giu73lfs Reopen - https://prnt.sc/OT4AaBiD7PfI https://prnt.sc/GbjGdZ2ckoF9
011 | Functional | Major | Portfolio Location >> Assets | Not able to update the data. |  | Actual Result: Edit Page - Not able to update data in any fields on assets page, getting required field validation on asset type and asset type dropdown is displaying as not editable. Expected Result: User should be able to update the data on the assets page. | QA Approved | Jeet | https://prnt.sc/4hbuwKxoLcU6
012 | Functional | Major | Portfolio Location >> Threshold Amount | Threshold amount is not updating. |  | Actual Result: When update the threshold amount from any number to "0" then it is not updating. Expected Result: It should update the value when user enter only "0". | QA Approved | Hitarth | https://prnt.sc/0dz1YtxO7syZ
013 | Functional | Minor | Tenant Panel >> Create service request | Not able to type in Service Type, Asset Type/ Problem Area, and Problem Details fields. |  | Actual Result: Dropdown is displaying in Service Type, Asset Type/ Problem Area, and Problem Details fields. Expected Result: It should display the text box and when user type then dropdown should narrow down,data should diplay according the entered data. | QA Approved | Jeet | https://prnt.sc/3Z-OAetyyrQv |  | Type functionality not implemented in create service request
014 | Functional | Major | Customize | Fields are not displaying. |  | Actual Result: Response time and rectification time are not displaying in FM admin as view purpose. Expected Result: Response time and rectification time should display in FM admin as view purpose. | QA Approved | Hitarth | FM Admin: https://prnt.sc/AoQjMSMODVGR VCG Admin: https://prnt.sc/KBplUYQnBTv0 |  | Customize chnages are not implement in fm admin.
015 | Functional | Minor | Call center user & FM Admin >> Service request >> Notes | Notes not displaying in proper aligment. |  | Actual Result: Create Service request - View page - Added notes is not displaying in proper aligment. Expected Result: Call center user and FM Admin - Description and notes should display in 2 to 3 line on view page. | QA Approved | Jeet | FM Admin: https://prnt.sc/DASduHvANr3E Call center: https://prnt.sc/9-_dMx6pqIyo
016 | Functional | Minor | Email >> Induction content | Text in induction content expired email is not proper. |  | Actual Result: Induction Content - Email - Text in email is not proper when induction content is expiry. Expected Result: It should displat like, Dear FM Admin, We would like to inform you that induction content for the job location named 'Ahmedabad' with the title 'Induction_One' is set to expire in 1 day. We kindly request you to update induction content at your earliest convenience. Thank you for your prompt attention to this matter. Sincerely, QDIS FM Team | QA Approved | Hitarth | https://prnt.sc/1FTMpOFCTeIR
017 | Suggestion | Minor | Email >> Induction content | It better to show the induction date. |  | Actual Result: Induction date is not displaying in induction content. Expected Result: Induction date should display so FM admin able to know the correct date. | QA Approved | Hitarth | https://prnt.sc/z85w8KrOQTWU
018 | Functional | Minor | Email >> Contractor certificate | Text in contractor certificate expired email is not proper. |  | Actual Result: Contractor certificate - Text in email is not proper when contractor certificate is expiry. Expected Result: It should display like, Dear contractor, We would like to inform you that your certificate with the reference 'mj' is scheduled to expire in 1 month. We kindly request you to update your certificate at your earliest convenience. Thank you for your prompt attention to this matter. Sincerely, QDIS FM Team | QA Approved | Hitarth
019 | Functional | Major | Add new vendor | Getting 404 bad request after clicking on add button of vendor creation page. |  | Actual result: getting 404 bad request error while creating new vendor management. Expected result: It should create vendor successfully and should not show any error. | QA Approved | Hitarth |  | Unable to reproduce this bug
020 | Functional | Major | Job location >> Tenant | Not able to update the tenant details in job location. |  | Actual Result: Not able to update the tenant details in job location. Expected Result: User should be able to update the details in tenant. | QA Approved | Hitarth | https://prnt.sc/PLFkI-EynYeZ
021 | Suggestion | Minor | Job location >> Asset | Asset image is not properly displaying. |  | Actual Result: Asset image is not properly displaying. Expected Result: Asset image should display proper in the view page. | QA Approved | Jeet | https://prnt.sc/ZO7aZezdw9Ja
022 | Design | Minor | VCG Admin >> Priorities | Add some space |  | Actual Result: Less space displaying between rectification time field and text box. Expected Result: Add some space between rectification time field and text box. | QA Approved | Jeet | https://prnt.sc/HSlvH-03UTUm
023 | Suggestion | Major | FM Admin >> Service request | Asset details like asset type is not displaying. |  | Actual Result: Asset details or asset id is not displaying in the service request details screen. Expected Result: It should display the asset ID or asset details so that the user can identify the service request created for a specific asset. | Todo | Ravi | https://prnt.sc/WndcLSy5Llrd
024 | Functional | Major | Tenant Panel >> Service request details | Asset type / problem area is not displaying. |  | Actual Result: Not receiving any data in asset type / problem area field on view page. Expected Result: It should display the asset type / problem area in the view page which is added while creating service request. | QA Approved | Hitarth | https://prnt.sc/W6NwNZLyB4JV
025 | Functional | Major | Tenant and call center user panel >> Create service request | Room number is not displaying. |  | Actual Result: Create service request & view page - Room number of asset is not displaying. Expected Result: Room number for that asset should display. | Todo | Jeet | https://prnt.sc/LO_lc43AyEsS https://prnt.sc/EPdhWsu-A_Eg
026 | Functional | Major | Tenant panel >> Profile | Room no., floor no. and lease expiry date is not displaying. |  | Actual Result: Room no., floor no. and lease expiry date is not displaying. Expected Result: Room no., floor no. and lease expiry date should display in profile. | Todo | Jeet | https://prnt.sc/R2WOOcgIRoxR
027 | Suggestion | Major | VCG>>service request | FM provider name is not showing in view page of service request. |  | Actual Result: FM provider name is not showing in view page of service request. Expected Result: FM provider name should be displayed in the view page. | Todo | Jeet | https://prnt.sc/mWUAv9f9D24p
028 | Suggestion | Major | FM>>Issue management | Issue in FM should get deleted, which is created from VCG and not assigned. |  | Actual Result: In FM Issue should is not getting deleted which is not assigned but deleted from VCG. Expected Result: In FM Issue should be deleted, if it is deleted from VCG and not assigned. | Todo | Jeet
029 | Suggestion | Major | VCG>>Contact us queries | FM provider name and sub FM is not showing in view page of Contact Us queries. |  | Actual Result: In FM Issue should is not getting deleted which is not assigned but deleted from VCG. Expected Result: In FM Issue should be deleted, if it is deleted from VCG and not assigned. | Todo | Jeet | https://prnt.sc/KdPj37h7vcYi